# Technical Roadmap — KIRT

Authoritative source: KIRT Technical Roadmap - Pre-Build to Demo-Ready.docx

This file summarizes the roadmap. For the detailed, dependency-sequenced execution plan with pre-build gates, parallel workstreams, exit criteria, risk register, and owner assignments, refer to the source document.

## Current State

| Artifact | Status |
| --- | --- |
| Unified Synthesis Document | Complete |
| Initiative Discovery Document | Complete |
| Architecture Decisions | Confirmed |
| Foundation Data Layer (POC) | ~90% Complete |
| Reference POC Tooling | Functional / design input for KIRT |
| KIRT Application Code | Not Started — greenfield build |
| Organizational Approval | Not obtained — pending Gate 1 |
| Legal Boundaries | Not obtained — pending Gate 3 |
| Template Ground Truth | Not collected — pending Gate 4 |
| Cost Model | Not estimated |

## Pre-Build Gates (Weeks 1-4)

All four must clear before committing development resources:

| Gate | Owner | Target | Status |
| --- | --- | --- | --- |
| 1. Executive Alignment | Carlos Marques | Weeks 1-2 | Pending |
| 2. IT/AI Governance | Dr. Jonathan Gough | Weeks 1-2 | Pending |
| 3. Legal Boundaries | Jonathan → Sean Colicchio | Weeks 2-3 | Pending |
| 4. Template Ground Truth | Caleb Crisci | Weeks 2-4 | Pending |

## Parallel Workstreams (During Gates)

| Workstream | Owner | Target |
| --- | --- | --- |
| Data normalization prototype | Roy + Jonathan + Caleb | Week 4 |
| Cost model (3 scales) | Roy + Jonathan | Weeks 3-4 |
| Application architecture plan (KIRT greenfield) | Roy | Weeks 3-4 |
| Effort baseline measurement | Caleb | Weeks 2-4 |
| Synthetic data strategy | Roy + Jonathan | Weeks 3-4 |
| SharePoint repository setup | Carlos | Weeks 1-2 |
| Red Hat FlightPath materials | Roy | Weeks 3-4 |

## Build Phases (Post-Gate)

### Phase A: Foundation Data Layer Completion — Weeks 5-8

Complete and harden Foundation. Core infra is ~90% built; finish ingestion pipelines, deploy entity resolution, stand up APIs for KIRT consumption.

Exit criteria: Ingest SF CSV + SP folder, resolve customer entities across both, serve normalized data via internal API.

### Phase B: KIRT Intelligence Layer — Weeks 7-12

Build user-facing intelligence on top of Foundation data. Overlaps with Phase A.

Exit criteria: User can log in via SSO, search across data, generate Account Brief and Engagement Prep, upload meeting notes.

### Phase C: Demo-Ready Polish — Weeks 11-14

Harden for demonstration. Load synthetic data, run through real-world scenarios, refine output quality.

Exit criteria: Non-technical stakeholder can watch live demo of all 4 Day-1 outputs using synthetic data and understand the value without explanation. Demo runs reliably on 3 consecutive attempts.

## What “Demo-Ready” Means

Must-haves: Live SSO login, natural language search, Account Brief in <60s, Engagement Prep, Client Doc generation, Cross-sell recommendations, human-in-the-loop editing, auto-generated architecture docs.

Should-haves: Side-by-side manual vs. KIRT comparison, multiple persona views, upload-to-insight flow, data provenance.

Explicitly not in demo: Real customer data, BSE/SOW generation, SF direct API, email/calendar, proactive alerting, production-scale performance.

## Total Timeline

~14 weeks to demo-ready, assuming gates clear by Week 4. If gates delayed, build phases shift but internal sequencing stays the same.

## References

- Detailed execution plan: KIRT Technical Roadmap - Pre-Build to Demo-Ready.docx (this directory)

- Foundation architecture: architecture.html (this directory, Forge Foundation v3.0)

- Current vs. target infrastructure: current-vs-target.md

- KIRT architecture reference: Strategic Account Framework - KIRT Architecture.html (this directory)